## ICO control sheet
ICO Project Schedule | [9 empty] | Gantt Chart Template © 2006-2018 by Vertex42.com.
J-play
| Project Start Date | 2018-09-17 |  |  |  |  | Display Week | 1 |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8
| Project Lead | Denny/ Sam L. | [7 empty] | 2018-09-17 | [6 empty] | 2018-09-24 | [6 empty] | 2018-10-01 | [6 empty] | 2018-10-08 | [6 empty] | 2018-10-15 | [6 empty] | 2018-10-22 | [6 empty] | 2018-10-29 | [6 empty] | 2018-11-05
 | time axis 2018-09-17 to 2018-11-11
WBS | TASK | LEAD | Check Ready | OWNER | START | END | DAYS | % DONE | WORK DAYS | time axis 2018-09-17 to 2018-11-11
1 | Pre ICO Documents Preparation |  | N |  | 2018-09-17 | 2018-10-16 | 30 | 11.11% | 22
1.1 | Whit papers | [Name] | Y | [Name] | 2018-09-17 | 2018-09-17 | 1 | 100% | 1
1.1.1 | Chinese version |  | Y |  | 2018-09-17 | 2018-09-17 | 1 | 100% | 1
1.1.2 | English version |  | Y |  | 2018-09-17 | 2018-09-17 | 1 | 100% | 1
1.1.3 | Other version |  | Y |  | 2018-09-17 | 2018-09-17 | 1 | 100% | 1
1.1.4 | Developing Road Map |  | Y |  | 2018-09-17 | 2018-09-18 | 2 | 100% | 2
1.1.5 | Developing Road Map |  | Y |  | 2018-09-17 | 2018-09-18 | 2 | 100% | 2
1.1.6 | Company Road Map |  | Y |  | 2018-09-17 | 2018-09-17 | 1 | 100% | 1
1.1.7 | Roles and responsiblities |  | Y |  | 2018-09-17 | 2018-09-18 | 2 | 100% | 2
1.1.8 | Accountability |  | Y |  | 2018-09-17 | 2018-09-21 | 5 | 100% | 5
1.1.9 | Technical info |  | Y |  | 2018-09-17 | 2018-09-23 | 7 | 100% | 5
1.1.10 | System info |  | Y |  | 2018-09-17 | 2018-09-19 | 3 | 100% | 3
1.1.11 | Team info |  | Y |  | 2018-09-17 | 2018-09-19 | 3 | 100% | 3
1.1.12 | Budget |  | Y |  | 2018-09-17 | 2018-09-21 | 5 | 100% | 5
1.2 | Token info |  | N |  | 2018-09-17 | 2018-09-21 | 5 | 0% | 5
1.2.1 | Token Management Team |  | N |  | 2018-09-17 | 2018-09-19 | 3 | 0% | 3
1.2.1.1 | Total supply |  | N |  | 2018-09-17 | 2018-09-21 | 5 | 0% | 5
1.2.1.2 | Token Economy |  | N |  | 2018-09-17 | 2018-09-21 | 5 | 0% | 5
1.2.1.3 | Token Allocations |  | N |  | 2018-09-17 | 2018-09-21 | 5 | 0% | 5
1.3 | Business Plan |  | N |  | 2018-09-17 | 2018-09-19 | 3 | 0% | 3
1.3.1 | Business Plan CHT ver. |  | N |  | 2018-09-17 | 2018-09-18 | 2 | 0% | 2
1.3.2 | Business Plan ENG ver. |  | N |  | 2018-09-17 | 2018-09-19 | 3 | 0% | 3
1.3.3 | Discription of the pre-ICO |  | N |  | 2018-09-17 | 2018-09-19 | 3 | 0% | 3
1.3.4 | Partners and Advisors |  | N |  | 2018-09-17 | 2018-09-18 | 2 | 0% | 2
1.3.5 | Social Channels |  | N |  | 2018-09-17 | 2018-09-23 | 7 | 0% | 5
1.4 | Governance & Controls |  | N |  | 2018-09-17 | 2018-09-30 | 14 | 0% | 10
1.4.1 | Clear processes and procedures |  | N |  | 2018-09-17 | 2018-09-30 | 14 | 0% | 10
1.4.2 | Transparency and accountability |  | N |  | 2018-09-17 | 2018-09-30 | 14 | 0% | 10
1.4.3 | Clear framework of escalation and operation |  | N |  | 2018-09-17 | 2018-09-30 | 14 | 0% | 10
1.5 | Smart Contract |  | N |  | 2018-09-17 | 2018-09-19 | 3 | 0% | 3
1.5.1 | Pre-ICO Contracts |  | N |  | 2018-09-17 | 2018-09-19 | 3 | 0% | 3
1.5.2 | ICO Smart Contract |  | N |  | 2018-09-17 | 2018-09-19 | 3 | 0% | 3
1.5.3 | Reservation Contract. |  | N |  | 2018-09-17 | 2018-09-19 | 3 | 0% | 3
1.5.4 | Pre-Audits by third parties |  | N |  | 2018-09-17 | 2018-09-19 | 3 | 0% | 3
1.5.5 | Bug Bounty |  | N |  | 2018-09-17 | 2018-09-23 | 7 | 0% | 5
1.6 | Legal |  | N |  | 2018-09-17 | 2018-09-19 | 3 | 0% | 3
1.6.1 | Local Reputable Law Firm |  | N |  | 2018-09-17 | 2018-09-19 | 3 | 0% | 3
1.6.2 | Legal consideration |  | N |  | 2018-09-17 | 2018-09-19 | 3 | 0% | 3
1.6.3 | Is the token issued during the ICO a security or not |  | N |  | 2018-09-17 | 2018-09-17 | 1 | 0% | 1
1.6.4 | Are you using SAFT |  | N |  | 2018-09-17 | 2018-09-17 | 1 | 0% | 1
1.6.5 | Offering geo-fenced |  | N |  | 2018-09-17 | 2018-09-19 | 3 | 0% | 3
1.6.6 | Setting up a foundation to be a steward of the token |  | N |  | 2018-09-17 | 2018-09-30 | 14 | 0% | 10
1.6.7 | Subscruption Contract |  | N |  | 2018-09-17 | 2018-09-23 | 7 | 0% | 5
1.6.8 | Company Legal Status |  | N |  | 2018-09-17 | 2018-09-23 | 7 | 0% | 5
1.6.9 | Legal approval from the Local Law Firm |  | N |  | 2018-09-17 | 2018-10-16 | 30 | 0% | 22
1.6.10 | Legal clarification on all the public released contracts |  | N |  | 2018-09-17 | 2018-10-16 | 30 | 0% | 22
1.7 | Tax & Accounting |  | N |  | 2018-09-17 | 2018-09-23 | 7 | 0% | 5
1.7.1 | Tax footprint |  | N |  | 2018-09-17 | 2018-09-23 | 7 | 0% | 5
1.7.2 | Accounting framework and transfer pricing |  | N |  | 2018-09-17 | 2018-09-23 | 7 | 0% | 5
1.7.3 | Tax footprint of founders and investors |  | N |  | 2018-09-17 | 2018-09-23 | 7 | 0% | 5
1.8 | Investment Deck |  | N |  | 2018-09-17 | 2018-09-19 | 3 | 0% | 3
1.8.1 | 2-Pages DM |  | N |  | 2018-09-17 | 2018-09-18 | 2 | 0% | 2
1.8.2 | Investor Report PPT CHT ver. |  | N |  | 2018-09-17 | 2018-09-19 | 3 | 0% | 3
1.8.3 | Investor Report PPT ENG ver. |  | N |  | 2018-09-17 | 2018-09-19 | 3 | 0% | 3
1.9 | Public Paper |  | N |  | 2018-09-17 | 2018-09-19 | 3 | 0% | 3
1.9.1 | Chinese version |  | N |  | 2018-09-17 | 2018-09-19 | 3 | 0% | 3
1.9.2 | English version |  | N |  | 2018-09-17 | 2018-09-19 | 3 | 0% | 3
2 | Pre ICO Marketing Preparation |  | N |  | 2018-09-17 | 2018-10-31 | 45 | 45.47% | 33
2.1 | Marketing Stratege implant |  | N |  | 2018-09-17 | 2018-10-08 | 22 | 50% | 16
2.1.1 | Marketing Plan CHT ver. |  | N |  | 2018-09-17 | 2018-09-18 | 2 | 50% | 2
2.1.2 | Marketing Plan ENG ver. |  | N |  | 2018-09-17 | 2018-09-19 | 3 | 50% | 3
2.2 | Social media and community management |  | N |  | 2018-09-17 | 2018-10-08 | 22 | 50% | 16
2.2.1 | Internal communications |  | N |  | 2018-09-17 | 2018-09-18 | 2 | 50% | 2
2.2.2 | External communications |  | N |  | 2018-09-17 | 2018-09-19 | 3 | 50% | 3
2.3 | Registration |  | N |  | 2018-09-25 | 2018-10-08 | 14 | 36.42% | 10
2.3.1 | Landing Page for ICO |  | N |  | 2018-09-25 | 2018-09-26 | 2 | 50% | 2
2.3.2 | Tutorial for the registration |  | N |  | 2018-09-25 | 2018-10-01 | 7 | 50% | 5
2.3.3 | Tutorial video and blog post on how to participate |  | N |  | 2018-09-25 | 2018-10-08 | 14 | 50% | 10
2.3.4 | Write blog posts about every step of the process |  | N |  | 2018-09-25 | 2018-10-08 | 14 | 50% | 10
2.3.5 | Create explainer videos to show how to purchase tokens. |  | N |  | 2018-09-25 | 2018-10-01 | 7 | 50% | 5
2.3.6 | Livestream video Q&A |  | N |  | 2018-09-25 | 2018-10-09 | 15 | 50% | 11
2.3.7 | Community management x100, be ready |  | N |  | 2018-09-25 | 2018-10-09 | 15 | 0% | 11
2.3.8 | Watch out for all potential hackers. |  | N |  | 2018-09-25 | 2018-10-01 | 7 | 0% | 5
3 | KYC/ AML White lists |  | N |  | 2018-09-30 | 2018-10-31 | 32 | 0% | 23
3.1 | Framework |  | N |  | 2018-09-30 | 2018-10-03 | 4 | 0% | 3
3.2 | Compliance with relevant regulatory requirements |  | N |  | 2018-09-25 | 2018-09-27 | 3 | 0% | 3
3.3 | Third Parties verification |  | N |  | 2018-09-20 | 2018-09-26 | 7 | 0% | 5
3.4 | KYC/ AML Landing pages |  | N |  | 2018-09-30 | 2018-10-06 | 7 | 0% | 5
3.5 | Screening |  | N |  | 2018-09-30 | 2018-10-06 | 7 | 0% | 5
3.6 | Sanctions list monitoring |  | N |  | 2018-09-30 | 2018-10-02 | 3 | 0% | 2
3.7 | Risk Based Framwork |  | N |  | 2018-09-30 | 2018-10-06 | 7 | 0% | 5
4 | ICO Pre-sale |  | N |  | 2018-10-01 | 2018-10-31 | 31 | 0% | 23
4.1 | Pre-sale whitelist |  | N |  | 2018-10-01 | 2018-10-03 | 3 | 0% | 3
4.2 | AirDrop |  | N |  | 2018-10-01 | 2018-10-03 | 3 | 0% | 3
4.3 | Event/Seminar |  | N |  | 2018-10-01 | 2018-10-01 | 1 | 0% | 1
5 | ICO Lunch Day (Issuance) |  | N |  | 2018-10-15 | 2018-10-31 | 17 | 0% | 13
5.1 | Community management x1000, be ready |  | N |  | 2018-10-15 | 2018-10-21 | 7 | 0% | 5
5.2 | Watch out for all attack vector |  | N |  | 2018-10-01 | 2018-10-30 | 30 | 0% | 22
5.3 | Livestream at the comletion of the ICO |  | N |  | 2018-10-15 | 2018-10-17 | 3 | 0% | 3
5.4 | Offical ICO website |  | N |  | 2018-09-30 | 2018-10-06 | 7 | 0% | 5
6 | Post ICO |  | N |  | 2018-10-31 | 2018-10-31 | 1 | 0% | 1
6.1 | [Task] |  | N |  | 2018-10-31 | 2018-10-31 | 1 | 0% | 1
6.2 | [Task] |  | N |  | 2018-10-31 | 2018-10-31 | 1 | 0% | 1
6.3 | [Task] |  | N |  | 2018-10-31 | 2018-10-31 | 1 | 0% | 1
6.4 | [Task] |  | N |  | 2018-10-31 | 2018-10-31 | 1 | 0% | 1
6.5 | [Task] |  | N |  | 2018-10-31 | 2018-10-31 | 1 | 0% | 1
-
TEMPLATE ROWS
See the Help worksheet to learn how to use these rows. You can hide these rows before printing.
1 | [ Level 1 Task or Phase ] |  | N |  |  | - |  |  | -
1.1 | . [ Level 2 Task ] |  | N |  |  | - |  |  | -
1.1.1 | . . [ Level 3 Task ] |  | N |  |  | - |  |  | -
1.1.1.1 | . . . [ Level 4 Task ] |  | N |  |  | - |  |  | -
Note on A7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on B7: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C7: Task Lead Enter the name of the Task Lead in this column.
Note on D7: If indicated with NO, please specify in next worksheet
Note on E7: Owner Enter the name of the Owner in this column.
Note on F7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on G7: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on H7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on I7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on J7: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.
Note on B18: Technical info, e.g. Inner workings of application
Note on B19: System info, e.g. how the whole system works
Note on B20: Personal introduction; include: Telegram, Line, email, and ect.
Note on B22: Token info, e.g. how the token will be used within the system.
Note on B40: Only If Applicable
Note on B41: Only If Applicable
Note on B44: With incorporating blockchain companies/foundations and running an ICO process to advise you on your process
Note on B53: ensure relevant risk and tax language is inserted in documents
Note on B72: If you are doing a registration system based ICO, release all of the details and have people register beforehand.
Note on B75: Remind people to NOT send in their contributions from an exchange, they need to send it in from a wallet in which they control the private keys.
Note on B77: Create explainer videos to show how to purchase tokens. You need at least a semi-professional 2– 3 minute video with professional voice talent. Set this to private and don’t release it till the day of the ICO.
Note on B79: you will get an enormous amount of questions leading up to the ICO.
Note on B94: On the day of and the days leading up to your ICO, the whole team is basically going to need to be on call 24/7.
Note on B95: shut down Slack if you need to.
Note on B97: Keep sharing the tutorial videos you have created for how to participate. Limit the sources of truth to one place where people find the information they need to contribute.

## 工作表2
TEMPLATE ROWS
See the Help worksheet to learn how to use these rows. You can hide these rows before printing.
1 | [ Level 1 Task or Phase ] | N | - | -
1.1 | . [ Level 2 Task ] | N | - | -
1.1.1 | . . [ Level 3 Task ] | N | - | -
1.1.1.1 | . . . [ Level 4 Task ] | N | - | -